## VD
Resource Allocation- 29th May to 11th June'26
Name | Story Points | Standard Hour | Leaves in this Sprint | Dependencies | Remarks If Any
Backend
Vishal Gupta | 56 | 56 | 1 Leave |  | Reporting, TRD credation
Satish | 56 | 56 | 1 Leave |  | LPL BRE, Meetings and Crif Audit
Ahishek Gupta | 68 | 64 |  |  | Credit builder, Decentro, TRD Creation and Ball created for BBPS
Vedant | 64 | 64 |  |  | LAP Discussion andTask Breakdown
Aakash | 22 | 56 | 2 Leave |  | Credit Builder, Spark Tg, Finsense (Planning to give LAP)
Sumit Kumar | 24 | 72 |  |  | Finsense, Card Stack, TU Json Parsing changes
Rohit Raj | 82 | 56 | 2 Leave |  | Crif Audit, Crif Audit Feedback, LPL BEE integration in the BRE service, , Beuro Backend Admit Panel, , Beuro Backend Admit Panel
Aayush | 72 | 72 |  |  | Cibil Fetch Logic Change, Disbursal Automation
Avinash Kumar
Ankit Yadav | 48 | 72 |  |  | CONCERSIGNT, Scale up, Payme Website, credit Assist, viranchi Blog, Investment
Pawan Yadav | 72 | 72 |  |  | web loan 2.0 code refactor
Pooja Verma | 61.5 | 72 |  |  | CML Link Runner Events, payme-ca->create similar to MMB(web loan , ekyc, esign)
Vaibhav | 50 | 72 |  |  | Finsense, Payme Website- Drop Down
Payme App
Manit Choudhary | 40 | 56 |  | 1 Leave | BRE Validation, refetch cibil logic change for Payme and MMb, Link Runner Integration, MMB atribution logic change,
Sarika | 50 | 72 |  |  | Crashes, Loan History Screen Changes, Link Runner SDK Integration CML
Abhishek Vamja | 34 | 72 |  |  | Crashes, Loan History Screen Changes

## Sheet2
Resource | Task- In hand
| Vedant | LAP (Analysing LAP requirement)
| Aakash | Credit Builder/Spark Tg
| Sumit | finsense/setu
| Aayush | Setu/MMB Disbursal automation Export sync/websocket debug- Payment stus update in Credit assist
| Rohit | BRE/Observance/Criff
| list of tasks- Product | List of Task- Integration
| LAP | Easebuzz E-NACH Presentment Integration with CRM |  |  | VIshal Gupta- | Add one rule of BRE
| Disbursal Tracking in CRM | Experian Integration |  |  |  | finkurve auto disbursal go live
| Automatic Disbursal Reconsiliation | Collection suite changes
| update checkout calculation formula | GA 4 events and Atribution checks
Finkurve disbursal Automation
CRM > Pending Bank Verification Tracker > Summary Cards
| Resource Name |  | Start Date | no. of Days Dev Effrort
| Vishal Gupta | Create reporting system from legacy reports in paymeindia | 28th May 2026 | 16
| Satish Pandey | LPL BRE | 2nd June 2026 | 6
| Aayush Rawal | Disbursal tracking Automation | 29th June 2026 | 9
| Aayush Rawal | Cibil Refetch Logic Change | 1st June 2026 | 4
| Aakash | Spark Tg (remaining work) | 3rd June | 1
Abhishek Gupta